COMP-8117 · Splash Project Plan

The "Success Disaster"

Scaling in-house GenAI inference from 0 to a launch-day spike, on a startup budget

Team: [names + roles]

Status: Draft v0.1, week 2. Orange text marks things we still need to confirm or fill in.

# 1. Problem statement

One line: How can a bootstrapped startup serve its own GenAI model to a sudden spike of users without paying for idle GPUs and without crashing?

Startups that run their own models (fine-tuned LLMs, vision models, RAG pipelines) usually rent dedicated GPU machines. These cost roughly $3,000–$10,000+ a month and sit idle most of the time. On launch day, though, traffic can jump from almost zero to tens of thousands of users. Under-provision and the launch crashes. Over-provision and the company burns its runway. We call this the "Success Disaster".

This is not a made-up problem for us. At work I deploy in-house models on AWS and RunPod, and this tradeoff comes up every time we plan for growth.

## Our quest

Design, build and measure a small but real architecture that decouples the web tier from the GPU tier, queues requests instead of rejecting them, and scales GPU workers up with demand and back down to zero when idle. Then prove, with numbers, whether it beats an always-on GPU.

# 2. Why it matters (impact)

- Company: pay only for GPU seconds actually used, and survive a viral launch without burning funding ("cloud bankruptcy").

- Users: no "server overloaded" or gateway timeout errors; requests wait in a queue and get served with predictable latency.

- Engineering: a reusable pattern (gateway → queue → serverless GPU workers) that any small AI team could adopt.

# 3. The scenario we are simulating

To make this an engineering problem and not just a demo, we set fixed constraints, as if we were the startup's engineering team.

| Constraint | Value |
| --- | --- |
| Company | Fictional seed-stage startup launching one AI feature (e.g. image captioning or text summarization) |
| Launch day (deadline) | Our December defence |
| Team | [N] part-time engineers (us), 10 weeks |
| Budget | Splash is listed as "no budget". Plan A: free tiers and free credits only. Plan B: ask the professor for $30–$50 in credits, justified line by line. |
| Traffic target | Simulated spike from 0 to [e.g. 1,000] concurrent users |

# 4. Success criteria

We will call the project successful only if we can show these with measurements, not claims:

| # | Criterion | How we measure it |
| --- | --- | --- |
| 1 | No dropped requests during the spike | Locust error rate = 0% (or explained) |
| 2 | $0 idle cost | GPU workers at zero when no traffic; billing screenshots |
| 3 | Known cost per 1,000 requests | Provider billing ÷ requests served |
| 4 | Acceptable latency under load | p50 / p95 latency from Locust + our dashboard, target [X] s |
| 5 | Cheaper than the baseline at our traffic pattern | Same load against an always-on GPU; compare cost and latency |

# 5. Proposed architecture

- API gateway: small stateless FastAPI (or Node) service in a container. Accepts the request, puts a job on the queue, returns a job ID immediately.

- Queue: Redis. Holds jobs so a spike becomes a backlog, not a crash.

- GPU workers: serverless GPU (RunPod or Modal) running the model container. They pull jobs, run inference, write results, and scale to zero when the queue is empty.

- Results: client polls (or receives a webhook) using the job ID.

- Observability: dashboard showing queue depth, active workers, latency and cost over time.

- Baseline for comparison: the same model on one always-on GPU machine, no queue.

Main risks we already know about: GPU cold starts (seconds to minutes), queue growing faster than workers can drain it, and free-tier limits capping our tests.

# 6. Plan across 10 weeks

| Week | Phase | What we deliver |
| --- | --- | --- |
| 1–2 | Problem + team | Problem statement, alternatives considered, team formed, this plan |
| 3 | Research + design | Architecture diagram, tool choices with reasons, cost model on paper |
| 4–5 | Minimum working path | One request flows: API → queue → GPU worker → result |
| 6 | Scaling | Worker autoscaling and scale-to-zero working; queue behaviour under load |
| 7 | Load testing | Locust scenarios run; first real numbers (latency, errors, cost) |
| 8 | Baseline + fixes | Always-on GPU comparison; fix what broke in week 7 |
| 9 | Dashboard + write-up | Live dashboard, decisions log, final report draft |
| 10 | Defence prep | Rehearsed live demo + recorded backup demo, slides |

Note: week 4 excludes Fall Reading Week (Oct 10–18). Adjust dates once the official Splash milestones are confirmed.

# 7. Who does what

Work is split by ownership. Each person owns one part end to end and presents it at the defence, but everyone reviews each other's work.

| Role | Owner | Responsibilities |
| --- | --- | --- |
| Infra / DevOps | Abhinav | Containers, cloud deployment, autoscaling config, cost tracking, baseline setup |
| Backend + queue | [name] | API gateway, Redis queue, job status/results, error handling |
| AI / GPU worker | [name] | Model choice, model container, serverless GPU setup, cold-start measurements |
| Testing + dashboard + docs | [name] | Locust scenarios, metrics dashboard, report and slides |

## How we work together

- One weekly sync (30 min): what's done, what's blocked, what's next.

- One shared repo, with small pull requests reviewed by someone else.

- A decisions log: every significant choice gets a line with what we chose, what we rejected and why. This feeds both the defence and our individual skill-building reports.

# 8. What role does code play?

Code is necessary but it is not the main deliverable. The main deliverable is evidence that our design solves the problem:

- measured numbers (cost, latency, where it breaks);

- tradeoffs we can defend ("we used a queue because…", "cold starts cost us X seconds");

- what failed and how we fixed it.

So the code stays deliberately small: a prototype good enough to produce trustworthy measurements. We will not build a full product, user accounts or a polished frontend.

# 9. Resources and cost

| Item | Plan A (free) | Plan B (if credits allowed) |
| --- | --- | --- |
| API + queue hosting | Local Docker / AWS free tier | AWS App Runner or ECS + small Redis |
| GPU workers | RunPod / Modal free credits | Serverless GPU credits |
| Load testing | Locust (open source) | Same |
| Dashboard | Grafana Cloud free tier | Same |
| Total | $0 | $30–$50, justified per line |

For comparison: a dedicated GPU instance running 24/7 costs roughly $3,000–$10,000+ per month.

# 10. Alternatives we considered

Before committing, we ran three other problems through the same questions (problem, impact, cost, feasibility):

- Real-time fraud detection under 50 ms: strong problem, but a new domain for us and hard to demo convincingly.

- Zero-downtime database migration: very practical, but less connected to the AI/infra direction we want to grow in.

- Offline-first sync for field workers (CRDTs): interesting, but mostly client-side work and outside our team's strengths.

We chose the GenAI scaling problem because we have lived it, can measure it, and can defend it in December.

# 11. Risks

| Risk | What we will do |
| --- | --- |
| Budget rules don't allow credits | Plan A: free tiers only, smaller load numbers, explain the extrapolation |
| Cold starts too slow for the demo | Measure them, try warm pools / smaller models, report honestly |
| Live demo fails on the day | Recorded backup demo + saved dashboards |
| Scope too big for 10 weeks | Minimum path first (week 5); dashboard and baseline are cut-able extras |
| Uneven workload in the team | Clear ownership, weekly sync, decisions log |

# 12. Open questions for the professor

- Splash says "no budget". Can we use free credits, or request a small amount?

- What exactly is graded at the defence: demo, report, individual contribution?

- Are there official milestones or check-ins before December?